## Project Overview
Project Name: OpenCart Frontend Testing
Client: OpenCart
Test Environment: Demo OpenCart (https://demo.opencart.com)
Test Period: August 1-20, 2024
QA Team Lead: Pavan
Team Size: 3 members
Total Functionalities Tested: 31
Total Test Cases: 514
Overall Status: COMPLETED

## KPI Dashboard
KPI | Actual | Target | Status
Test Execution Rate | 100% | 100% | ✓ Met
Pass Rate | 89.1% | 93.0% | ✗ Below
Defect Detection Rate | 4.5% | 3.0% | ✗ Above
Test Coverage | 95.2% | 95.0% | ✓ Met
Critical Defects | 4 | 2 | ✗ Above
Blocked Test Cases | 31 | 14 | ✗ Above
Average Execution Time per Test | 15 mins | 10 mins | ✗ Above
Automation Coverage | 0% | 30% | ✗ Below

## Executive Summary
Project | Total_Test_Cases | Total_Functionalities | Executed_Test_Cases | Passed | Failed | Blocked | Overall_Pass_Rate_% | Test_Start_Date | Test_End_Date | Environment | Test_Lead | QA_Team_Size
OpenCart Frontend Testing | 514 | 31 | 514 | 458 | 25 | 31 | 89.1 | 01-Aug-2024 | 20-Aug-2024 | Demo OpenCart (https://demo.opencart.com) | Pavan | 3

## Weekly Progress
Week | Tests_Planned | Tests_Executed | Pass | Fail | Blocked | Pass_Rate_%
Week 1 (Aug 1-7) | 180 | 175 | 160 | 10 | 5 | 91.4
Week 2 (Aug 8-14) | 200 | 195 | 180 | 8 | 7 | 92.3
Week 3 (Aug 15-21) | 134 | 144 | 118 | 7 | 19 | 81.9

## Critical Issues
Bug_ID | Summary | Severity | Impact | Recommendation
OPENCART-BUG-17 | Future date accepted in Order Date field | Critical | High | Add date validation to prevent future dates
OPENCART-BUG-19 | Non-affiliate user can login via affiliate login | Critical | High | Implement proper affiliate account validation
OPENCART-BUG-20 | No options in Canon EOS 5D product dropdown | Critical | High | Fix product configuration for Canon EOS 5D
OPENCART-BUG-7 | User logged out on browser back button | Critical | Medium | Fix session management for browser navigation

## Risk Assessment
Functionality | Risk_Level | Defects_Found | Impact_on_Business | Mitigation_Required
Registration Process | High | 6 | High - User acquisition affected | Yes
Login/Authentication | High | 5 | High - User retention affected | Yes
Shopping Cart | Medium | 2 | Medium - Purchase process affected | Yes
Product Display | Medium | 2 | Medium - Product browsing affected | Yes
Contact Forms | Low | 1 | Low - Support channel affected | No

## Functionality Results
Functionality | Total | Executed | Passed | Failed | Blocked | Pass_Rate_%
Add to Cart | 9 | 9 | 9 | 0 | 0 | 100
Address Book | 21 | 21 | 21 | 0 | 0 | 100
Affiliate | 29 | 29 | 27 | 2 | 0 | 93.1
Change Password | 13 | 13 | 13 | 0 | 0 | 100
Checkout | 20 | 20 | 20 | 0 | 0 | 100
Contact Us | 13 | 13 | 12 | 1 | 0 | 92.3
Currencies | 3 | 3 | 3 | 0 | 0 | 100
Downloads | 13 | 13 | 11 | 0 | 2 | 84.6
Forgot Password | 25 | 25 | 9 | 1 | 15 | 36
Gift Certificate | 11 | 11 | 5 | 0 | 6 | 45.5
Header Menu Footer Options | 22 | 22 | 18 | 4 | 0 | 81.8
Home Page | 10 | 10 | 10 | 0 | 0 | 100
Login | 23 | 23 | 18 | 4 | 1 | 78.3
Logout | 11 | 11 | 9 | 2 | 0 | 81.8
My Account | 9 | 9 | 9 | 0 | 0 | 100
My Account Information | 13 | 13 | 13 | 0 | 0 | 100
Newsletter | 13 | 13 | 13 | 0 | 0 | 100
Order History | 12 | 12 | 12 | 0 | 0 | 100
Order Information | 8 | 8 | 8 | 0 | 0 | 100
Product Compare | 24 | 24 | 24 | 0 | 0 | 100
Product Display Page | 37 | 37 | 36 | 1 | 0 | 97.3
Product Returns | 11 | 11 | 10 | 1 | 0 | 90.9
Recurring Payments | 9 | 9 | 8 | 0 | 1 | 88.9
Register | 27 | 27 | 21 | 6 | 0 | 77.8
Returns | 17 | 17 | 17 | 0 | 0 | 100
Reward Points | 10 | 10 | 9 | 0 | 1 | 90
Search | 22 | 22 | 21 | 1 | 0 | 95.5
Shopping Cart | 33 | 33 | 26 | 2 | 5 | 78.8
Special Offers | 16 | 16 | 16 | 0 | 0 | 100
Transactions | 11 | 11 | 11 | 0 | 0 | 100
Wish List | 19 | 19 | 19 | 0 | 0 | 100

## Bug Summary
Metric | Count | Percentage
Total Bugs | 23 | 100
Critical Bugs | 4 | 17.4
Major Bugs | 7 | 30.4
Minor Bugs | 12 | 52.2
Open Bugs | 23 | 100
Fixed Bugs | 0 | 0